## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: 5 |  |  |  |  | Caglar Kurtkaya | ckurtk2@uic.edu
Week Of: 04/28/2019 |  |  |  |  | Aleksandar Knezevic | knezevi2@uic.edu
[5 empty] | Dayana Roa-Tapia | droata2@uic.edu
[5 empty] | Emily Lin | wlin48@uic.edu
| Item ID | Team Member | Last Week | This Week | Next Week | Issues
Server part of connection to game-- using Node.js |  | Caglar | research on Node.js | Start coding | let users see who is online when connecting
GUI part of game |  | Aleks | research on Node.js | set base GUI for pop-up windows | adding a scoring visual and allowing other players to see the player who is rolling's turn
Game logic |  | Dayana | research on Node.js | start coding | finish implementing game logic and activity diagram
Client part of game |  | Emily | research on Node.js | start coding | documentation and UML